## Sprint8
Key	Cat	Project	#Issue	Tid	ISP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10	RSP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10
	Any	Sprint8			0											13	25	23	22	22	21.5	18.5	18	13	13	13
	Back-end	Back-end			10											8	10	8	8	8	8	8	8	8	8	8
	Front-end	Front-end			0											0	0	0	0	0	0	0	0	0	0	0
	Firmware	Firmware			0											0	0	0	0	0	0	0	0	0	0	0
	Tests	Tests			0											0	0	0	0	0	0	0	0	0	0	0
	Neuroscripts	Neuroscripts			15											5	15	15	14	14	13.5	10.5	10	5	5	5
Key	Cat	Project	#Issue	Tid	ISP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10	RSP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10
PROJET1#4A	Neuroscripts	PROJET1	#4	A	15			1		0.5	3	0.5	5			5	15	15	14	14	13.5	10.5	10	5	5	5
PROJET1#4B	Tests	PROJET1	#4	B	0				3				1			0	0	0	0	0	0	0	0	0	0	0
PROJET1#3A	Back-end	PROJET1	#3	A	2		3									0	2	0	0	0	0	0	0	0	0	0
PROJET1#7B	Back-end	PROJET1	#7	B	5											5	5	5	5	5	5	5	5	5	5	5
PROJET1#7A	Back-end	PROJET1	#7	A	3											3	3	3	3	3	3	3	3	3	3	3
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
EE	EE	EE	EE	EE	EE	EE	EE
Days
Story Points
Days
Story Points

## Legends
Abbr	Designation	Description
US	User Story
SP	Story Points
ISP	Initial Story Points	Unit day
CSP	Current Story Points	Unit day	To be compared with the initial plan, updated when the task has been underestimated
RSP	Remaining Story Points	Unit day
Tid	Task Id	A, B, C, etc.

Gestion des sprints
A chaque jour préciser le travail effectué.
Si le temps est dépassé augmenter dans Tasks l’ISP pour le sprint en cours (recalcul de la charge de travail)
Rq : il faut modifier l’ISP global pour avoir une estimation complète de la tâche

Duplicates are forbidden in Sprints. Typo should change if it occurs !

## Dashboard
Overall tracking Split techno tracking

## User Stories
Project	#Issue	Title	Type	Priority	Sprint	ISP	CSP	RSP
PROJET1	#4	XXX1	Feature	100	7	8
PROJET1	#3	XXX2	Feature	100	7	5
PROJET1	#7	XXX3	Feature	100	7	8

## Tasks
Internal Configuration	Y-offset	10	X-offset	7

Key	Categories	Project	#Issue	Tid	Description	Priority	ISP	CSP	Present	Sprint9	Sprint8	Sprint7					SPRINT START : limit for dashboard
	Any	Tasks			0		41	41	DO NOT FILL	13	25	38					Please start a new file with fewer sprints.
	Back-end	Back-end			0		13	13		8	10	10
	Front-end	Front-end			0		0	0		0	0	0
	Firmware	Firmware			0		0	0		0	0	0
	Tests	Tests			0		3	3		0	0	3
	Neuroscripts	Neuroscripts			0		25	25		5	15	25
Key	Categories	Project	#Issue	Tid	Description	Priority	ISP	CSP	Present (NO DATA)	Sprint9	Sprint8	Sprint7
PROJET1#4A	Neuroscripts	PROJET1	#4	A	YYY1	115	25	25		5	15	25
PROJET1#4B	Tests	PROJET1	#4	B	YYY2	90	3	3		0	0	3
PROJET1#3A	Back-end	PROJET1	#3	A	YYY3	100	5	5		0	2	5
PROJET1#7A	Back-end	PROJET1	#7	A	YYY4	100	3	3		3	3
PROJET1#7B	Back-end	PROJET1	#7	B	YYY5	100	5	5		5	5	5

## Sprint7
Key	Cat	Project	#Issue	Tid	ISP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10	RSP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10
	Any	Sprint7			0											22	38	35	34	31	30.5	27.5	27	22	22	22
	Back-end	Back-end			10											7	10	7	7	7	7	7	7	7	7	7
	Front-end	Front-end			0											0	0	0	0	0	0	0	0	0	0	0
	Firmware	Firmware			0											0	0	0	0	0	0	0	0	0	0	0
	Tests	Tests			3											0	3	3	3	0	0	0	0	0	0	0
	Neuroscripts	Neuroscripts			25											15	25	25	24	24	23.5	20.5	20	15	15	15
Key	Cat	Project	#Issue	Tid	ISP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10	RSP	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8	Day9	Day10
PROJET1#4A	Neuroscripts	PROJET1	#4	A	25			1		0.5	3	0.5	5			15	25	25	24	24	23.5	20.5	20	15	15	15
PROJET1#4B	Tests	PROJET1	#4	B	3				3				1			0	3	3	3	0	0	0	0	0	0	0
PROJET1#3A	Back-end	PROJET1	#3	A	5		3									2	5	2	2	2	2	2	2	2	2	2
PROJET1#7B	Back-end	PROJET1	#7	B	5											5	5	5	5	5	5	5	5	5	5	5
PROJET1#7A	Back-end	PROJET1	#7	A	0											0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																0	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
																	0	0	0	0	0	0	0	0	0	0
EE	EE	EE	EE	EE	EE	EE	EE
Days
Story Points
Days
Story Points

## COMPUTATION
Sprints	2	1	0
SP			21

## PARAMETERS
Internal parameters

SprintX
Task-row-start	20
Task-row-end	220
RSP-column	17
Key-column	1

Tasks
Y-offset	10		Not used yet, see row 1 in Tasks
X-offset	7		Not used yet, see row 1 in Tasks

## Credits&Issues
Credits
This spreadsheet has been developed by Antoine de Rengervé

Updated	07/20/18

License
This spreadsheet is licensed under Creative Commons

XXXX

Issues
Auto computation of the RSP for each task and sprint
Display RSP graph per sprint
Display current sprint KPI in dashboard
Compute velocity of the team
Add default velocity
Parameterize according to presency
Configure all sprints by default because we want to display prediction and this requires to have them all displayed.
Always change the ISP in a dedicated area (RSP : Real SP) to allow to check a posteriori time spent on each task